## Sheet1
| Start date | Duration(days) | End date
Initial state
Project Plan | 2014-02-04 | 24 | 2014-02-27
Brainstorm ideas | 2014-02-04 | 7 | 2014-02-10
Questions compilation | 2014-02-04 | 7 | 2014-02-10
Target group research | 2014-02-05 | 2
Research the use of the software neded | 2014-02-07 | 3
Making drafts, sketches | 2014-02-11 | 5
Install needed software | 2014-02-09 | 3
Gather necesarry materials | 2014-02-15 | 14
Design
Functionality describtion | 2014-02-18 | 19 | 2014-02-21
Flow charts | 2014-02-18 | 20 | 2014-02-21
Website mapping | 2014-02-18 | 5 | 2014-02-22
Website wireframe(version 1) | 2014-02-25 | 4 | 2014-02-28
GUI application interfaces | 2014-03-10 | 21 | 2014-02-17
Initial database model
Determine purpose of the database | 2014-02-25 | 1
Organize the information | 2014-02-26 | 3
Divide information into tables | 2014-03-01 | 3
Set attributes | 2014-03-04 | 4
Specify Primary keys | 2014-03-08 | 2
Set up table relationships | 2014-03-10 | 2
Set normalization rules | 2014-03-12 | 3
Interaction design | 2014-02-10 | 14
Visual design | 2014-02-10 | 14
Website design(version 2) | 2014-02-17 | 14
Production
Final Database | 2014-03-14 | 14
Entrance Application | 2014-03-21 | 10
Shop Applications | 2014-03-14 | 21
Website fucntionality(version 3) | 2014-03-28 | 14
QR code system | 2014-03-14 | 7
Build prototype | 2014-03-28 | 7
Test the prototype | 2014-04-05 | 14
Finalize
Final appearance retouch | 2014-04-21 | 14
Debugging | 2014-05-05 | 14
Checking performance issues | 2014-04-14 | 7
Create user manual
Presenting
Presentation | 2014-05-25 | 7 | 2014-05-31